## Overview
To-Do List
TASK | PRIORITY | ESTIMATE(Day) | STATUS | START DATE | DUE DATE | % COMPLETE | DONE? | NOTES
VETC_Synchronization | High | 5 | In Progress |  | 2016-11-10 | 0% | 0
[6 empty] | 100% | 1
[6 empty] | 100% | 1
[6 empty] | 100% | 1
[6 empty] | 0% | 0
0
0

## SyncImageClient (hidden)
SyncImageClient
TASK | PRIORITY | STATUS | START DATE | DUE DATE | % COMPLETE | DONE? | NOTES
UploadLaneInImage | High | Complete | 2016-10-28 | 2016-11-09 | 100% | 1 | Done
UploadLaneOutImage | High | Complete | 2016-10-28 | 2016-11-09 | 100% | 1 | Done
DownloadLaneInImage | High | Complete | 2016-10-28 | 2016-11-09 | 100% | 1 | Done
SyncProcess | High | Complete | 2016-10-28 | 2016-11-09 | 100% | 1 | Improving
Optimize Sync Time | Normal | In Progress | 2016-11-10 | 2016-11-25 | 75% | 0 | Improving
0
0

## VETC_Synchronization
VETC_Synchronization
TASK | PRIORITY | ESTIMATE(Hour) | STATUS | START DATE | DUE DATE | OWNER | % COMPLETE | DONE? | NOTES
Main Window | Low | 5 | Complete | 08/03/2017 | 16/03/2017 |  | 75% | 0
Config Window | Low | 4 | Complete | 08/03/2017 | 16/03/2017 | Doanh | 75% | 0
Ftp transfer functions | High | 1 | Complete | 08/03/2017 | 16/03/2017 | Viet | 100% | 1
Job Managerment(Main Quartz) | High | 1 | Complete | 08/03/2017 | 16/03/2017 | Phong | 100% | 1
TollTicket MTC->ETC(Vé lượt) | Normal | 2 | Complete | 08/03/2017 | 16/03/2017 | Thang | 100% | 1
CommuterTicket MTC->ETC(Vé tháng quý) | Normal | 2 | Complete | 08/03/2017 | 16/03/2017 | Thang | 100% | 1
EmployeeData MTC->ETC | Normal | 2 | Complete | 08/03/2017 | 16/03/2017 | Ron | 100% | 1
VehiclePlateData MTC->ETC | Normal | 2 | Complete | 08/03/2017 | 16/03/2017 | Nhan | 100% | 1
EtagRegisterData ETC->MTC | Normal | 2 | Complete | 08/03/2017 | 16/03/2017 | Ron | 100% | 1
TollTicket Transaction ETC->MTC | Normal | 2 | Complete | 08/03/2017 | 16/03/2017 | Thang | 100% | 1
CommuterTransactionData ETC->MTC | Normal | 2 | Complete | 08/03/2017 | 16/03/2017 | Thang | 100% | 1
SpecicalTransactionData ETC-MTC(xe ưu tiên) | Normal | 2 | Complete | 08/03/2017 | 16/03/2017 | Nhan | 100% | 1
ETAGTransactionData ETC->MTC | Normal | 2 | Complete | 08/03/2017 | 16/03/2017 | Viet | 100% | 1
LaneImage ETC-MTC | Normal | 2 | Complete | 08/03/2017 | 16/03/2017 | Viet | 100% | 1
Recognization Image ETC-MTC | Normal | 2 | Complete | 08/03/2017 | 16/03/2017 | Viet | 100% | 1
AccessDatabase | Normal | 2 | In Progress | 08/03/2017 | 16/03/2017 |  | 100% | 1
Create Database(table,trigger, store) | Normal | 3 | Complete |  |  | Khuong | 100% | 1
SaveFile | High | 2 | Complete | 08/03/2017 | 16/03/2017 | Phong | 100% | 1
TollTicket MTC->FTP->ETC(Vé lượt) | High | 2 | Complete | 16/03/2017 | 20/03/2017 | Thang | 100% | 1
CommuterTicket MTC->FTP->ETC (Vé tháng quý) | High | 2 | Complete | 16/03/2017 | 20/03/2017 | Thang | 100% | 1
EmployeeData MTC->FTP->ETC | High | 2 | Complete | 16/03/2017 | 20/03/2017 | Ron | 100% | 1
VehiclePlateData MTC->FTP->ETC | High | 2 | Complete | 16/03/2017 | 20/03/2017 | Nhan | 100% | 1
EtagRegisterData ETC->FTP->MTC | High | 2 | Complete | 16/03/2017 | 20/03/2017 | Ron | 100% | 1
BoTaiChinh ETC->FTP->MTC | High | 2 | Complete | 16/03/2017 | 20/03/2017 | Nhan | 100% | 1
SpecicalTransactionData ETC->FTP->MTC(xe ưu tiên) | High | 2 | Complete | 16/03/2017 | 20/03/2017 | Nhan | 100% | 1
ETAGTransactionData ETC->FTP->MTC | High | 2 | Complete | 16/03/2017 | 20/03/2017 | Viet | 100% | 1
Image ETC->FTP->MTC | High | 2 | Complete | 16/03/2017 | 20/03/2017 | Viet | 100% | 1
TollTicketTransaction ETC->FTP->MTC | High | 2 | Complete | 16/03/2017 | 20/03/2017 | Thang | 100% | 1
CommuterTransactionData ETC->FTP->MTC | High | 2 | Complete | 16/03/2017 | 20/03/2017 | Thang | 100% | 1
100%